**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared: Jan 31, 2020 |

Report Prepared By: My Thuy Trang Le

Employer/Organization:

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | Tea Subscription Box App | |
| T02 | |
| Start Date: **Jan 20, 2020** | End Date: **Feb 02, 2020** |
| Green (Good) | |

Summary

|  |
| --- |
| **Project Status Summary** |
| As compared to our first Project Status Report, this status report mainly focuses on the development and finished stage design along with future development on enhancing what we already created in Project Status Report 1. We have continued developing the application and have generally completed goals and task on the given deadline. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Completing and testing for improvements for the UI of Customer side | Completing database of the application |
| Creating and modifying UI layouts of Admin side |  |
| Implementing navigation layout of Admin site |  |
| Making Login page and Register page work |  |
| Partialy creating connection between screen layouts and SQLite database of Customer side |  |

Upcoming Objectives for Feb 3, 2020, 2020 to Feb 23, 2020

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To | | Duration | Date |
| Implementing main features of Customer side | All team members | | 6 days | Feb 08, 2020 |
| Continue building database of the application | Kevin Teran | | 6 days | Feb 14, 2020 |
| Continue creating connection between screen layouts and SQLite database | All team members | | 4 days | Feb 18, 2020 |
| Implementing main features of Admin side | All team members | | 10 days | Feb 22, 2020 |
| Improving the application content | Chau Bui, My Thuy Trang Le | | 2 days | Feb 20, 2020 |
| Testing and debugging | All team members | | 2 days | Feb 22, 2020 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Functional screen layouts of Customer side | | Kevin Teran, My Thuy Trang Le | Feb 13, 2020 |
| Implementing features of Admin side | | All team members | Feb 22, 2020 |
| Completion of the application content | | Chau Bui, My Thuy Trang Le | Feb 20, 2020 |
| Completion of the database | | Kevin Teran | Feb 14, 2020 |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Development progress is not as efficient as the team want it to be due to conflicting personal schedules among team members. | The team will have a discussion about how to set project schedule that fits in with all members’ schedules.  Task plans and deadlines will be good tools that help the project progress stay in line with the plan. | Feb 08, 2020 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Insufficient time and heavy workload due to tight schedules of other courses’ projects and exams. | Hi | Hi | Planning all important tasks ahead of time is helpful since all members can expect what’s to come and be prepared for it.  All team members are willing to help and support each other during the busy time.  Extending deadlines will be considered if necessary. |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport1”.

For e.g. T36\_ProjectStatusReport2

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, Feb 02, 2020 (11:59 p.m.)**